## Sheet1 (2)
Company Name | Labor Category | On Contract (total #/Planned) | EOM Feb Accruals ($) | Planned 1 Mar-30 Apr Accruals | Planned to EOM Apr ($) | Delta ($) | Planned 1May-31 Jul | Funds needed thru Jul ($)
Analytics | Program Analyst VI | 1 of 1 | 51521.855 |  | 100910.04
Analytics | Program Analyst III | 2 of 2 | 97394 |  | 168036
DESE Research | Engineer/Scientist VII | 1 of 1 | 34380.5 |  | 84018
Nousystem | Engineer III | 1 of 1 | 82650.7 |  | 143637.45
Nousystem | Program/Systems Analyst III | 1 of 1 | 41994.18 |  | 64587.54
Nousystem | Program/Systems Analyst VI | 2 of 3 / 1 planned | 68073.39 |  | 232510.41
Nousystem | Senior Engineer III | 1 of 2 / 1 planned | 57221.32 |  | 204287.88
Nousystem | Engineer VIII | 3 of 3 | 211246.2 |  | 489495.6
Nousystem | Program/Systems Analyst IX | 2 of 2 | 102855.97 |  | 204287.88
Nousystem | Subject Matter Expert I | 1 of 1 | 59051.52 |  | 121332.42
Nousystem | Program/Systems Analyst V | 0 of 1 / 1 planned | 0 |  | 124875.03 |  |  |  | Will extend past EOM Jul
Nousystem | Program/Systems Analyst l | 1 of 1 | 32636.08 |  | 139944.93 |  |  |  | Will extend past EOM Jul this is a relative new hire
20000
|  | FY19 Hours Planned through EOM Feb | Hours Worked through EOM Feb | FY19 planned Accruals EOM Feb | Accruals Through EOM Feb | Delta from FY19 hour planned and hours work EOM Feb | Delta from FY19 spend plan to Accruals through EOM Feb | Hours remaining to be worked | Hours needed from FY19 EOM Apr plan to EOM Jul plan | Hours Needed minus credits |  | Required funding through EOM July
| Labor Category | [6 empty] | Hours |  |  | Rates
| Program Analyst VI | [9 empty] | 129.58
| Program Analyst III | [9 empty] | 107.9
| Engineer/Scientist VII | [9 empty] | 189.15
| Engineer III | [9 empty] | 83.33
| Program/Systems Analyst III | [9 empty] | 100
| Program/Systems Analyst VI | [9 empty] | 131.79
| Senior Engineer III | [9 empty] | 210.52
| Engineer VIII | [9 empty] | 156.55
| Program/Systems Analyst IX | [9 empty] | 161.12
| Subject Matter Expert I | [9 empty] | 180.56
| Program/Systems Analyst V | [9 empty] | 123.81
| Program/Systems Analyst l | [9 empty] | 70.63
Credit towards next plan
|  | Planned EOM APR | Worked | Remaining | Needed EOM 1 Mar-EOM Apr | credits
|  | 804 | 410.5
|  | 1608 | 932
|  | 804 | 329
|  | 789 | 454
|  | 789 | 513
|  | 2367 | 693
|  | 1578 | 442
|  | 2367 | 1021.5
|  | 1578 | 794.5
|  | 789 | 384
|  | 789 | 0
|  | 789 | 184

## FY19 PLAN
[12 empty] | 2080 |  |  | 160 |  |  | 160 |  |  | 168 |  |  | 152 |  |  | 168 |  |  | 176 |  |  | 176 |  |  | 168 |  |  | 184 |  |  | 176 |  |  | 160 |  |  | 176 |  |  | 160 | PLANNED |  |  | FUNDED TO DATE |  |  | REMAINING |  |  | TOTAL
1920
|  | W31P4Q 09 A 0021/0020 | [12 empty] | 156 |  |  | 156 |  |  | 164 |  |  | 148 |  |  | 164 |  |  | 172 |  |  | 172 |  |  | 156 |  |  | 172 |  |  | 172 |  |  | 156 |  |  | 172 |  |  | 156 | [6 empty] | TO BE FUNDED |  |  | THIS EXECUTION
[11 empty] | TO 20 |  |  |  | 2018-11-01 |  |  | 2018-12-01 |  |  | 2019-01-01 |  |  | 2019-02-01 |  |  | 2019-03-01 |  |  | 2019-04-01 |  |  | 2019-05-01 |  |  | 2019-06-01 |  |  | 2019-07-01 |  |  | 2019-08-01 |  |  | 2019-09-01 |  |  | 2019-10-01 |  |  | 2019-11-19 | TOTALS |  |  | TOTALS |  |  | TOTALS
PROG |  | LABOR CATEGORY |  | SITE | CONTRACTOR | TYPE | FIRST | NAME | LOE | SLIN | DATE RANGE | RATE | DATE RANGE | RATE | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS |  | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS
OTA | CATEGORY | Program Analyst VI | PSS | ON | Analytix, LLC | Sub | Hamilton | Holliday | 1 |  | 8/26/18-8/25/19 | 125.51 | 8/26/19-8/25/20 | 129.58
OTA | CATEGORY | Program Analyst III | PSS | ON | Analytix, LLC | Sub | Carl | Marlow | 1 |  | 8/26/18-8/25/19 | 104.5 | 8/26/19-8/25/20 | 107.9
OTA | CATEGORY | Program Analyst III | PSS | ON | Analytix, LLC | Sub | Audrey | McGee | 1 |  | 8/26/18-8/25/19 | 104.5 | 8/26/19-8/25/20 | 107.9
OTA | CATEGORY | Engineer/Scientist VII | PSS | ON | DESE Research, Inc. | TM | Moody | Parsons | 1 |  | 5/9/18-5/8/19 | 182.05 | 5/9/19-5/8/20 | 189.15
OTA | CATEGORY | Engineer III | PSS | ON | nou Systems, Inc. | TM | Victoria | Kirk | 1 |  | 5/9/18-5/8/19 | 81.86 | 5/9/19-5/8/20 | 83.33
OTA | CATEGORY | Program/Systems Analyst III | PSS | ON | nou Systems, Inc. | TM | Brian | Glickman | 1 |  | 5/9/18-5/8/19 | 98.23 | 5/9/19-5/8/20 | 100
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM | Gregg | Freese | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79
OTA | CATEGORY | Senior Engineer III | PSS | ON | nou Systems, Inc. | TM | Anamaria | Dent | 1 |  | 5/9/18-5/8/19 | 206.8 | 5/9/19-5/8/20 | 210.52
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM | Megan | Tyler | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Jason | Grimmett | 1 |  | 5/9/18-5/8/19 | 153.78 | 5/9/19-5/8/20 | 156.55
OTA | CATEGORY | Program/Systems Analyst IX | PSS | ON | nou Systems, Inc. | TM | Jason | Boswell | 1 |  | 5/9/18-5/8/19 | 158.27 | 5/9/19-5/8/20 | 161.12
OTA | CATEGORY | Subject Matter Expert I | PSS | ON | nou Systems, Inc. | TM | Matt | Tucker | 1 |  | 5/9/18-5/8/19 | 177.37 | 5/9/19-5/8/20 | 180.56
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Patrick | Williams | 1 |  | 5/9/18-5/8/20 | 153.78 | 5/9/19-5/8/21 | 156.55
OTA | CATEGORY | Senior Engineer III | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/19 | 206.8 | 5/9/19-5/8/20 | 210.52
OTA | CATEGORY | Program/Systems Analyst IX | PSS | ON | nou Systems, Inc. | TM | David | Walsh | 1 |  | 5/9/18-5/8/19 | 158.27 | 5/9/19-5/8/20 | 161.12 | [46 empty] | Travel |  | 0
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Jim | Head | 1 |  | 5/9/18-5/8/19 | 153.78 | 5/9/19-5/8/20 | 156.55 | [46 empty] | Total
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79
OTA | CATEGORY | Program/Systems Analyst V | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/24 | 121.62 | 5/9/19-5/8/25 | 123.81
OTA | CATEGORY | Program/Systems Analyst l | PSS | ON | nou Systems, Inc. | TM | Zoe | Dancer | 1 |  | 5/9/18-5/8/25 | 69.38 | 5/9/19-5/8/26 | 70.63
[52 empty] | Travel |  | 36336
Total
G&A
[52 empty] | Funded |  | 2141623.52
Remaining
[5 empty] | PID | [46 empty] | HOURS |  | DOLLARS
|  | DB-04 801 |  |  | 205989 |  | Doug | Parsons | 0.75 |  |  | 108.16
|  | DE-03 301 |  |  | 434849 |  | Scott | Patrick | 0.5 |  |  | 108.16
|  | DB-03 854 |  |  | 203954 |  | Curtis | Conkey | 1 |  |  | 108.16
[7 empty] | David | Ellsworth | 1 |  |  | 108.16
|  | DB-03 |  |  |  |  | Ryan | Miller | 1 |  |  | 108.16
|  | DB-03 801 |  |  | 434518 |  | Anna | McColloch | 1 |  |  | 108.16
|  | DB-03 854 |  |  | 205898 |  | Matt | Stoos | 1 |  |  | 108.16
|  | DB-04 |  |  |  |  | Chris | Davis | 1 |  |  | 108.16
[52 empty] | Total Reim | With Fees
[52 empty] | Grand | Total
PID
|  | DB-04 801 |  |  | 205989 |  | Doug | Parsons | 0.5 |  |  | 144.93
|  | DE-03 301 |  |  | 434849 |  | Scott | Patrick | 0.5 |  |  | 110.19
|  | DB-03 854 |  |  | 203954 |  | Curtis | Conkey | 1 |  |  | 103.41
[7 empty] | David | Ellsworth | 1 |  |  | 77.06
|  | DB-03 |  |  |  |  | Ryan | Miller | 1 |  |  | 103.41
|  | DB-03 801 |  |  | 434518 |  | Anna | McColloch | 1 |  |  | 103.41
|  | DB-03 854 |  |  | 205898 |  | Matt | Stoos | 1 |  |  | 103.41
|  | DB-04 |  |  |  |  | Chris | Davis | 1 |  |  | 103.41
Catherine
|  | Summer |  |  |  |  | Nathan | Singleton | [43 empty] | Total Reim | With Fees
|  | December/Summer Intern |  |  |  |  | Daniel | [44 empty] | Grand | Total
|  | Spring |  |  |  |  | Larry
DC Labor & Travel
[45 empty] | 210000 | [6 empty] | x.035 | [11 empty] | Old fees
[16 empty] | 791070.53 | [35 empty] | x.027
[15 empty] | 2363 | [36 empty] | Gov cost
[15 empty] | G&A | 57823.84 | [35 empty] | gov+G&A
[15 empty] | fees | [32 empty] | received | 732000 |  |  | gov+G&Ax.02
[52 empty] | abov-gov cost | [11 empty] | new fees
7 month Reim need
7 month DC need

## nSI rate comp (hidden)
| TO 11 |  | TO 20 |  |  | Delta
|  | 8/26/17-8/25/18 |  | 5/9/17-5/8/18 | 5/9/18-5/8/19
Kirk | Program/Systems Analyst V | 114.44 | Engineer III | 80.41 | 81.86
TenBrink | Program/Systems Analyst VII | 128.15 | Program/Systems Analyst III | 96.5 | 98.23
McIntosh | Program/Systems Analyst VII | 128.15 | Program/Systems Analyst V | 119.47 | 121.62
Dent | Program/Systems Analyst IX | 164.03 | Senior Engineer III | 203.14 | 206.8
Tyler | Program/Systems Analyst IX | 164.03 | Program/Systems Analyst VI | 127.17 | 129.46
Grimmett | Program/Systems Analyst IX | 164.03 | Engineer VIII | 151.06 | 153.78
Boswell | Program/Systems Analyst IX | 164.03 | Program/Systems Analyst IX | 155.47 | 158.27
Tucker | Program/Systems Analyst IX | 164.03 | Subject Matter Expert I | 174.23 | 177.37

## FY19 CONTRACT ACTIONS
TO 20 | Cost Center | TIN Letters | MIPR | MIPR AMOUNT | PoP Start | PoP End | MOD | AWARD | SLIN | SLIN |  | HOURS | PRON | WBS | PAN
[10 empty] | LABOR | TRAVEL
TT2120190024 |  | - | HQ0147967210 | 2141623.52 | 2018-11-21 | 2019-10-31 | 38 | 2018NOV30 |  | 0002ME | 0003DD | 15276 | R2933914RV | D.0002019.210 | R20029119
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z
WBS | Cost Center | TIN | MIPR | MIPR AMOUNT | POP Start | POP End |  | AWARD Date
LETTER
A.0039976.7.3 | 40488166 | - | HQ0147966843 | 791070.53 | 2018-11-21 | 2018-10-31 |  | 2018-11-21
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z

## COL Report
Direct Cite | [5 empty] | Reimbursable | [5 empty] | DC Travel
Month | Spend Plan | Monthly Accruals.1 | Cumulative Accruals | Funded | Planned Ceiling |  | Spend Plan | Monthly Accruals.2 | Cumulative Accruals | Funded | Planned Ceiling |  | Spend Plan | Monthly Accruals.3 | Cumulative Accruals | Funded | Planned Ceiling
2018-11-15 | 0 | 0 |  | 2126483.52 |  | 2018-11-15 | 85200.37 | 85200.37 |  | 791070.53 |  | 2018-11-15 | 0 | 0 |  | 15140 | 36336
2018-12-15 |  | 202148.65 |  | 2126483.52 |  | 2018-12-15 |  | 92883.99 |  | 791070.53 |  | 2018-12-15 | 3028 | 3412.26 |  | 15140 | 36336
2019-01-15 |  | 347778.02 |  | 2126483.52 |  | 2019-01-15 |  | 113826.56 |  | 791070.53 |  | 2019-01-15 |  | 1614.02 |  | 15140 | 36336
2019-02-15 |  | 291269.24 |  | 2126483.52 |  | 2019-02-15 |  | 117747.06 |  | 791070.53 |  | 2019-02-15 |  | 1997.31 |  | 15140 | 36336
2019-03-15 |  |  |  | 2126483.52 |  | 2019-03-15 |  |  |  | 791070.53 |  | 2019-03-15 |  |  |  | 15140 | 36336
2019-04-15 |  |  |  | 2126483.52 |  | 2019-04-15 |  |  |  | 791070.53 |  | 2019-04-15 |  |  |  | 15140 | 36336
2019-05-15 | [5 empty] | 2019-05-15 | [5 empty] | 2019-05-15 |  |  |  |  | 36336
2019-06-15 | [5 empty] | 2019-06-15 | [5 empty] | 2019-06-15 |  |  |  |  | 36336
2019-07-15 | [5 empty] | 2019-07-15 | [5 empty] | 2019-07-15 |  |  |  |  | 36336
2019-08-15 | [5 empty] | 2019-08-15 | [5 empty] | 2019-08-15 |  |  |  |  | 36336
2019-09-15 | [5 empty] | 2019-09-15 | [5 empty] | 2019-09-15 |  |  |  |  | 36336
2019-10-15 | [5 empty] | 2019-10-15 | [5 empty] | 2019-10-15 |  |  |  |  | 36336
2019-11-15 | [5 empty] | 2019-11-15 | [5 empty] | 2019-11-15 |  |  |  |  | 36336
Travel | 36336 |  |  |  |  | P_Fees | [5 empty] | Total
Total | [5 empty] | P_Total
791070.53
15511.19
57823.84
23552.99

## Hours
Direct Cite Hours
|  |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov
Labor Category | Current Hours | FTE | Planned | Worked.12 | Planned.1 | Worked.1 | Planned.2 | Worked.2 | Planned.3 | Worked.3 | Planned.4 | Worked.4 | Planned.5 | Worked.5 | Planned.6 | Worked.6 | Planned.7 | Worked.7 | Planned.8 | Worked.8 | Planned.9 | Worked.9 | Planned.10 | Worked.10 | Planned.11 | Worked.11 | Unnamed: 27
ENGINEER/SCIENTIST VII | 143.5 | 1 | 156 | 92 | 164 | 173 | 148 | 143.5 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
ENGINEER III | 146.5 | 2 | 312 | 275.5 | 328 | 338.5 | 296 | 146.5 | 328 |  | 344 |  | 344 |  | 312 |  | 344 |  | 344 |  | 312 |  | 344 |  | 312
ENGINEER VIII | 379 | 1 | 156 | 20.5 | 164 | 165 | 148 | 379 | 164 |  | 172 |  | 169 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
PROGRAM SYSTEMS ANALYST III TM | 152 | 1 | 153 | 139.5 | 161 | 168 | 145 | 152 | 161 |  | 169 |  | 169 |  | 153 |  | 169 |  | 169 |  | 153 |  | 169 |  | 153
PROGRAM SYSTEMS ANALYST VI- TM | 274 | 1 | 153 | 134 | 161 | 227 | 145 | 274 | 161 |  | 169 |  | 169 |  | 153 |  | 169 |  | 169 |  | 153 |  | 169 |  | 153
PROGRAM SYSTEMS ANALYST IX | 253.5 | 3 | 459 | 107 | 483 | 312 | 435 | 253.5 | 483 |  | 507 |  | 507 |  | 459 |  | 507 |  | 507 |  | 459 |  | 507 |  | 459
SUBJECT MATTER EXPERT I | 136.5 | 2 | 306 | 132.5 | 322 | 171 | 290 | 136.5 | 322 |  | 338 |  | 338 |  | 306 |  | 338 |  | 338 |  | 306 |  | 338 |  | 306
SR ENGINEER III | 138.5 | 3 | 459 | 238 | 483 | 404.5 | 435 | 138.5 | 483 |  | 507 |  | 507 |  | 459 |  | 507 |  | 507 |  | 459 |  | 507 |  | 459
PROGRAM ANALSYT III | 318 | 2 | 306 | 205.5 | 322 | 335.5 | 290 | 318 | 322 |  | 338 |  | 338 |  | 306 |  | 338 |  | 338 |  | 306 |  | 338 |  | 306
PROGRAM ANALSYT VI | 145.5 | 1 | 153 | 79.5 | 161 | 168 | 145 | 145.5 | 161 |  | 169 |  | 169 |  | 153 |  | 169 |  | 169 |  | 153 |  | 169 |  | 153
PROGRAM SYSTEMS ANALYST V | nou Systems, Inc. | 1 | 153 | 0 | 161 | 0 | 145 |  | 161 |  | 169 |  | 169 |  | 153 |  | 169 |  | 169 |  | 153 |  | 169 |  | 153
PROGRAM SYSTEMS ANALYST I | nou Systems, Inc. | 1 | 153 | 130 | 161 | 54 | 145 |  | 161 |  | 169 |  | 169 |  | 153 |  | 169 |  | 169 |  | 153 |  | 169 |  | 153
Cumulative - Direct Cite Hours |  |  | Cumulative-Dec |  | Cumulative-Jan |  | Cumulative-Feb |  | Cumulative-Mar |  | Cumulative-Apr |  | Cumulative-May |  | Cumulative-Jun |  | Cumulative-Jul |  | Cumulative-Aug |  | Cumulative-Sep |  | Cumulative-Oct |  | Cumulative-Nov |  | Ceiling
Labor Category | Company | FTE | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
PROGRAM ANALYST VI | Analytix, LLC | 1
PROGRAM ANALYST III | Analytix, LLC | 2
ENGINEER/SCIENTIST VII | DESE Research, Inc. | 1
ENGINEER III | nou Systems, Inc. | 1
PROGRAM SYSTEMS ANALYST III TM | nou Systems, Inc. | 1
PROGRAM SYSTEMS ANALYST VI- TM | nou Systems, Inc. | 3
SR ENGINEER III | nou Systems, Inc. | 2
ENGINEER VIII | nou Systems, Inc. | 3
PROGRAM SYSTEMS ANALYST IX | nou Systems, Inc. | 2
SUBJECT MATTER EXPERT I | nou Systems, Inc. | 1
PROGRAM SYSTEMS ANALYST V | nou Systems, Inc. | 1
PROGRAM SYSTEMS ANALYST I | nou Systems, Inc. | 1
|  |  | Prog/Sys Analyst IX |  | Prog/Sys Analyst VI |  | Prog/Sys Analyst V |  | Prog/Sys Analyst III |  | Prog/Sys Analyst l
|  |  | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
|  |  | Senior Engineer III |  | Engineer VIII |  | Engineer III |  | Subject Matter Expert I
|  |  | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
|  |  | Planned | Worked | Planned | Worked
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Engineer/Scientist VII
|  |  | Planned | Worked
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov

## EOM Nov Drill
Cumulative - Direct Cite Hours | Cumulative-Dec |  | Dec-Delta | Cumulative-Jan |  | Jan-Delta | Cumulative-Feb |  | Feb-Delta
Labor Category | Planned | Worked |  | Planned | Worked |  | Planned | Worked
Program Analyst VI | 156 | 92 |  | 320 | 265 |  | 468 | 410.5
Program Analyst III | 312 | 275.5 |  | 640 | 614 |  | 936 | 932
Engineer/Scientist VII | 156 | 20.5 |  | 320 | 185.5 |  | 468 | 329
Engineer III | 156 | 139.5 |  | 320 | 307.5 |  | 468 | 454
Program/Systems Analyst III | 156 | 134 |  | 320 | 361 |  | 468 | 513
Program/Systems Analyst VI | 468 | 107 |  | 960 | 419 |  | 1404 | 693
Senior Engineer III | 312 | 132.5 |  | 640 | 303.5 |  | 936 | 442
Engineer VIII | 468 | 238 |  | 960 | 642.5 |  | 1404 | 1021.5
Program/Systems Analyst IX | 312 | 205.5 |  | 640 | 541 |  | 936 | 794.5
Subject Matter Expert I | 156 | 79.5 |  | 320 | 247.5 |  | 468 | 384
Program/Systems Analyst V | 156 | 0 |  | 320 | 0 |  | 468 | 0
Program/Systems Analyst l | 156 | 130 |  | 320 | 184 |  | 468 | 184
| Cumulative-Mar | Cumulative-Apr | Cumulative-May | Cumulative-Jun | Cumulative-Jul | Cumulative-Aug | Cumulative-Sep | Cumulative-Oct | Cumulative-Nov | Cumulative | Cumulative | Cumulative | Cumulative | Min 1960 | Min 1920 | Plan
Labor Category | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Unworked | Funded | Unfunded | Credit | Required | Required | EOM Nov
Program Analyst VI | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Program Analyst III | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920
Engineer/Scientist VII | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | [6 empty] | 993
Engineer III | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Program/Systems Analyst III | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Program/Systems Analyst VI | 1896 | 2412 | 2928 | 3396 | 3912 | 4428 | 4896 | 5412 | 5880
Senior Engineer III | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920
Engineer VIII | 1896 | 2412 | 2928 | 3396 | 3912 | 4428 | 4896 | 5412 | 5880
Program/Systems Analyst IX | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920
Subject Matter Expert I | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Program/Systems Analyst V | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Program/Systems Analyst l | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960
Plan
Labor Category | Hours | Rates | Funding
Program Analyst VI | 1098.5 | 129.58
Program Analyst III | 2308 | 107.9
Engineer/Scientist VII | 993 | 189.15
Engineer III | 1102 | 83.33
Program/Systems Analyst III | 1161 | 100
Program/Systems Analyst VI | 2717 | 131.79
Senior Engineer III | 1778 | 210.52
Engineer VIII | 3045.5 | 156.55
Program/Systems Analyst IX | 2130.5 | 161.12
Subject Matter Expert I | 1032 | 180.56
Program/Systems Analyst V | 648 | 123.81
Program/Systems Analyst l | 832 | 70.63
Total Labor
|  | Travel | 35000
Surge
Total

## nSI realignment (hidden)
[5 empty] | CURRENT | ADJ | NEW
PROG |  | LABOR CATEGORY | CONTRACTOR | LOE | HOURS | HOURS | HOURS
OTA | CATEGORY | Systems Analyst V | nou Systems, Inc. | 1 | 452 | -149
OTA | CATEGORY | Program Analyst VII | nou Systems, Inc. | 1.5 | 187 | 206
OTA | CATEGORY | Program Analyst IX | nou Systems, Inc. | 5 | 782 | -57