## FY19 PLAN
[12 empty] | 2080 |  |  | 160 |  |  | 160 |  |  | 168 |  |  | 152 |  |  | 168 |  |  | 176 |  |  | 176 |  |  | 168 |  |  | 184 |  |  | 176 |  |  | 160 |  |  | 176 |  |  | 160 |  |  | PLANNED |  |  | FUNDED TO DATE |  |  | REMAINING |  |  | TOTAL
[12 empty] | 1960 |  |  | 156 |  |  | 156 |  |  | 164 |  |  | 148 |  |  | 164 |  |  | 172 |  |  | 172 |  |  | 156 |  |  | 172 |  |  | 172 |  |  | 156 |  |  | 172 |  |  | 156
|  | W31P4Q 09 A 0021/0020 | [57 empty] | TO BE FUNDED |  |  | THIS EXECUTION
[11 empty] | TO 20 |  |  |  | 2018-11-01 |  |  | 2018-12-01 |  |  | 2019-01-01 |  |  | 2019-02-01 |  |  | 2019-03-01 |  |  | 2019-04-01 |  |  | 2019-05-01 |  |  | 2019-06-01 |  |  | 2019-07-01 |  |  | 2019-08-01 |  |  | 2019-09-01 |  |  | 2019-10-01 |  |  | 2019-11-19 |  |  | TOTALS |  |  | TOTALS |  |  | TOTALS
PROG |  | LABOR CATEGORY |  | SITE | CONTRACTOR | TYPE | FIRST | NAME | LOE | SLIN | DATE RANGE | RATE | DATE RANGE | RATE | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS |  |  |  | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS | HOURS | HOURS | DOLLARS
OTA | CATEGORY | Program Analyst VI | PSS | ON | Analytix, LLC | Sub | Hamilton | Holliday | 1 |  | 8/26/18-8/25/19 | 125.51 | 8/26/19-8/25/20 | 129.58 |  |  | 0 | 156 |  | 19579.56 | 164 |  | 20583.64 | 148 |  | 18575.48 | 164 |  | 20583.64 | 172 |  | 21587.72 | 172 |  | 21587.72 | 156 |  | 19579.56 | 172 |  | 21587.72 | 132 | 40 | 21750.52 |  | 156 | 20214.48 |  | 172 | 22287.76 |  | 156 | 20214.48 | 1436 | 368 | 248132.28 |  |  |  | 1436 | 368 | 248132.28
OTA | CATEGORY | Program Analyst III | PSS | ON | Analytix, LLC | Sub | Carl | Marlow | 1 |  | 8/26/18-8/25/19 | 104.5 | 8/26/19-8/25/20 | 107.9 |  |  | 0 | 156 |  | 16302 | 164 |  | 17138 | 148 |  | 15466 | 164 |  | 17138 | 172 |  | 17974 | 172 |  | 17974 | 156 |  | 16302 | 172 |  | 17974 | 132 | 40 | 18110 |  | 156 | 16832.4 |  | 172 | 18558.8 |  | 156 | 16832.4 | 1436 | 368 | 206601.6 |  |  |  | 1436 | 368 | 206601.6
OTA | CATEGORY | Program Analyst III | PSS | ON | Analytix, LLC | Sub | Audrey | McGee | 1 |  | 8/26/18-8/25/19 | 104.5 | 8/26/19-8/25/20 | 107.9 |  |  | 0 | 156 |  | 16302 | 164 |  | 17138 | 148 |  | 15466 | 164 |  | 17138 | 172 |  | 17974 | 172 |  | 17974 | 156 |  | 16302 | 172 |  | 17974 | 132 | 40 | 18110 |  | 156 | 16832.4 |  | 172 | 18558.8 |  | 156 | 16832.4 | 1436 | 368 | 206601.6 |  |  |  | 1436 | 368 | 206601.6 |  |  |  | 392389.44
OTA | CATEGORY | Engineer/Scientist VII | PSS | ON | DESE Research, Inc. | TM | Moody | Parsons | 1 |  | 5/9/18-5/8/19 | 182.05 | 5/9/19-5/8/20 | 189.15 |  |  | 0 | 156 |  | 28399.8 | 164 |  | 29856.2 | 148 |  | 26943.4 | 164 |  | 29856.2 | 172 |  | 31312.6 | 48 | 124 | 32193 |  | 156 | 29507.4 |  | 172 | 32533.8 |  | 172 | 32533.8 |  | 156 | 29507.4 |  | 172 | 32533.8 |  | 156 | 29507.4 | 852 | 952 | 364684.8 |  |  |  | 852 | 952 | 364684.8 |  |  |  | 187825.95
OTA | CATEGORY | Engineer III | PSS | ON | nou Systems, Inc. | TM | Victoria | Kirk | 1 |  | 5/9/18-5/8/19 | 81.86 | 5/9/19-5/8/20 | 83.33 |  |  | 0 | 156 |  | 12770.16 | 164 |  | 13425.04 | 148 |  | 12115.28 | 164 |  | 13425.04 | 172 |  | 14079.92 | 48 | 124 | 14262.2 |  | 156 | 12999.48 |  | 172 | 14332.76 |  | 172 | 14332.76 |  | 156 | 12999.48 |  | 172 | 14332.76 |  | 156 | 12999.48 | 852 | 952 | 162074.36 |  |  |  | 852 | 952 | 162074.36
OTA | CATEGORY | Program/Systems Analyst III | PSS | ON | nou Systems, Inc. | TM | Brian | Glickman | 1 |  | 5/9/18-5/8/19 | 98.23 | 5/9/19-5/8/20 | 100 |  |  | 0 | 156 |  | 15323.88 | 164 |  | 16109.72 | 148 |  | 14538.04 | 164 |  | 16109.72 | 172 |  | 16895.56 | 48 | 124 | 17115.04 |  | 156 | 15600 |  | 172 | 17200 |  | 172 | 17200 |  | 156 | 15600 |  | 172 | 17200 |  | 156 | 15600 | 852 | 952 | 194491.96 |  |  |  | 852 | 952 | 194491.96
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM | Gregg | Freese | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79 |  |  | 0 | 156 |  | 20195.76 | 164 |  | 21231.44 | 148 |  | 19160.08 | 164 |  | 21231.44 | 172 |  | 22267.12 | 48 | 124 | 22556.04 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 172 | 22667.88 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 156 | 20559.24 | 852 | 952 | 256323.24 |  |  |  | 852 | 952 | 256323.24
OTA | CATEGORY | Senior Engineer III | PSS | ON | nou Systems, Inc. | TM | Anamaria | Dent | 1 |  | 5/9/18-5/8/19 | 206.8 | 5/9/19-5/8/20 | 210.52 |  |  | 0 | 156 |  | 32260.8 | 164 |  | 33915.2 | 148 |  | 30606.4 | 164 |  | 33915.2 | 172 |  | 35569.6 | 48 | 124 | 36030.88 |  | 156 | 32841.12 |  | 172 | 36209.44 |  | 172 | 36209.44 |  | 156 | 32841.12 |  | 172 | 36209.44 |  | 156 | 32841.12 | 852 | 952 | 409449.76 |  |  |  | 852 | 952 | 409449.76
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM | Megan | Tyler | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79 |  |  | 0 | 156 |  | 20195.76 | 164 |  | 21231.44 | 148 |  | 19160.08 | 164 |  | 21231.44 | 172 |  | 22267.12 | 48 | 124 | 22556.04 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 172 | 22667.88 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 156 | 20559.24 | 852 | 952 | 256323.24 |  |  |  | 852 | 952 | 256323.24
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Jason | Grimmett | 1 |  | 5/9/18-5/8/19 | 153.78 | 5/9/19-5/8/20 | 156.55 |  |  | 0 | 156 |  | 23989.68 | 164 |  | 25219.92 | 148 |  | 22759.44 | 164 |  | 25219.92 | 172 |  | 26450.16 | 48 | 124 | 26793.64 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 172 | 26926.6 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 156 | 24421.8 | 852 | 952 | 304477.96 |  |  |  | 852 | 952 | 304477.96
OTA | CATEGORY | Program/Systems Analyst IX | PSS | ON | nou Systems, Inc. | TM | Jason | Boswell | 1 |  | 5/9/18-5/8/19 | 158.27 | 5/9/19-5/8/20 | 161.12 |  |  | 0 | 156 |  | 24690.12 | 164 |  | 25956.28 | 148 |  | 23423.96 | 164 |  | 25956.28 | 172 |  | 27222.44 | 48 | 124 | 27575.84 |  | 156 | 25134.72 |  | 172 | 27712.64 |  | 172 | 27712.64 |  | 156 | 25134.72 |  | 172 | 27712.64 |  | 156 | 25134.72 | 852 | 952 | 313367 |  |  |  | 852 | 952 | 313367
OTA | CATEGORY | Subject Matter Expert I | PSS | ON | nou Systems, Inc. | TM | Matt | Tucker | 1 |  | 5/9/18-5/8/19 | 177.37 | 5/9/19-5/8/20 | 180.56 |  |  | 0 | 156 |  | 27669.72 | 164 |  | 29088.68 | 148 |  | 26250.76 | 164 |  | 29088.68 | 172 |  | 30507.64 | 48 | 124 | 30903.2 |  | 156 | 28167.36 |  | 172 | 31056.32 |  | 172 | 31056.32 |  | 156 | 28167.36 |  | 172 | 31056.32 |  | 156 | 28167.36 | 852 | 952 | 351179.72 |  |  |  | 852 | 952 | 351179.72
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Patrick | Williams | 1 |  | 5/9/18-5/8/20 | 153.78 | 5/9/19-5/8/21 | 156.55 |  |  | 0 | 156 |  | 23989.68 | 164 |  | 25219.92 | 148 |  | 22759.44 | 164 |  | 25219.92 | 172 |  | 26450.16 | 48 | 124 | 26793.64 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 172 | 26926.6 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 156 | 24421.8 | 852 | 952 | 304477.96
OTA | CATEGORY | Senior Engineer III | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/19 | 206.8 | 5/9/19-5/8/20 | 210.52 |  |  | 0 | 156 |  | 32260.8 | 164 |  | 33915.2 | 148 |  | 30606.4 | 164 |  | 33915.2 | 172 |  | 35569.6 | 48 | 124 | 36030.88 |  | 156 | 32841.12 |  | 172 | 36209.44 |  | 172 | 36209.44 |  | 156 | 32841.12 |  | 172 | 36209.44 |  | 156 | 32841.12 | 852 | 952 | 409449.76 | 0 | 0 | 0 | 11976 | 9672 | 3273707.52 | 0 | 0 | 0
OTA | CATEGORY | Program/Systems Analyst IX | PSS | ON | nou Systems, Inc. | TM | David | Walsh | 1 |  | 5/9/18-5/8/19 | 158.27 | 5/9/19-5/8/20 | 161.12 |  |  | 0 | 156 |  | 24690.12 | 164 |  | 25956.28 | 148 |  | 23423.96 | 164 |  | 25956.28 | 172 |  | 27222.44 | 48 | 124 | 27575.84 |  | 156 | 25134.72 |  | 172 | 27712.64 |  | 172 | 27712.64 |  | 156 | 25134.72 |  | 172 | 27712.64 |  | 156 | 25134.72 | 852 | 952 | 313367 | [6 empty] | Travel |  | 0
OTA | CATEGORY | Engineer VIII | PSS | ON | nou Systems, Inc. | TM | Jim | Head | 1 |  | 5/9/18-5/8/19 | 153.78 | 5/9/19-5/8/20 | 156.55 |  |  | 0 | 156 |  | 23989.68 | 164 |  | 25219.92 | 148 |  | 22759.44 | 164 |  | 25219.92 | 172 |  | 26450.16 | 48 | 124 | 26793.64 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 172 | 26926.6 |  | 156 | 24421.8 |  | 172 | 26926.6 |  | 156 | 24421.8 | 852 | 952 | 304477.96 | [6 empty] | Total |  | 0
OTA | CATEGORY | Program/Systems Analyst VI | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/19 | 129.46 | 5/9/19-5/8/20 | 131.79 |  |  | 0 | 156 |  | 20195.76 | 164 |  | 21231.44 | 148 |  | 19160.08 | 164 |  | 21231.44 | 172 |  | 22267.12 | 48 | 124 | 22556.04 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 172 | 22667.88 |  | 156 | 20559.24 |  | 172 | 22667.88 |  | 156 | 20559.24 | 852 | 952 | 256323.24
OTA | CATEGORY | Program/Systems Analyst V | PSS | ON | nou Systems, Inc. | TM |  |  | 1 |  | 5/9/18-5/8/24 | 121.62 | 5/9/19-5/8/25 | 123.81 |  |  | 0 | 156 |  | 18972.72 | 164 |  | 19945.68 | 148 |  | 17999.76 | 164 |  | 19945.68 | 172 |  | 20918.64 | 48 | 124 | 21190.2 |  | 156 | 19314.36 |  | 172 | 21295.32 |  | 172 | 21295.32 |  | 156 | 19314.36 |  | 172 | 21295.32 |  | 156 | 19314.36 | 852 | 952 | 240801.72
OTA | CATEGORY | Program/Systems Analyst l | PSS | ON | nou Systems, Inc. | TM | Zoe | Dancer | 1 |  | 5/9/18-5/8/25 | 69.38 | 5/9/19-5/8/26 | 70.63 |  |  | 0 | 156 |  | 10823.28 | 164 |  | 11378.32 | 148 |  | 10268.24 | 164 |  | 11378.32 | 172 |  | 11933.36 | 48 | 124 | 12088.36 |  | 156 | 11018.28 |  | 172 | 12148.36 |  | 172 | 12148.36 |  | 156 | 11018.28 |  | 172 | 12148.36 |  | 156 | 11018.28 | 852 | 952 | 137369.8 | [9 empty] | 2201963.92
[9 empty] | 19 | [5 empty] | 0 | 0 | 0 | 2964 | 0 | 412601.28 | 3116 | 0 | 433760.32 | 2812 | 0 | 391442.24 | 3116 | 0 | 433760.32 | 3268 | 0 | 454919.36 | 1284 | 1984 | 460550.2 | 468 | 2496 | 419685.24 | 516 | 2752 | 462729.88 | 396 | 2872 | 463164.68 | 0 | 2964 | 421380.96 | 0 | 3268 | 464599.52 |  | 2964 | 421380.96 | 17940 | 16336 | 5239974.96 | [9 empty] | 2782179.31
[54 empty] | Travel |  | 36336 | [9 empty] | 36196
[54 empty] | Total |  | 5276310.96 | [9 empty] | 2818375.31
[54 empty] | G&A |  | 142460.3959 | [9 empty] | 76096.1334
[54 empty] | Funded |  | 2141623.52
[54 empty] | Remaining |  | 3134687.44 | [9 empty] | 316312.13
[5 empty] | PID | [48 empty] | HOURS |  | DOLLARS
|  | DB-04 801 |  |  | 205989 |  | Doug | Parsons | 0.75 |  | 159000 | 108.16 |  |  |  |  | 0 | 117 |  | 12654.72 | 123 |  | 13303.68 | 111 |  | 12005.76 | 123 |  | 13303.68 | 129 |  | 13952.64 | 129 |  | 13952.64 | 117 |  | 12654.72 | 129 |  | 13952.64 | 129 |  | 13952.64 | 117 |  | 12654.72 | 129 |  | 13952.64 | 117 |  | 12654.72 | 1353 |  | 158995.2
|  | DE-03 301 |  |  | 434849 |  | Scott | Patrick | 0.5 |  | 106000 | 108.16 |  |  |  |  | 0 | 78 |  | 8436.48 | 82 |  | 8869.12 | 74 |  | 8003.84 | 82 |  | 8869.12 | 86 |  | 9301.76 | 86 |  | 9301.76 | 78 |  | 8436.48 | 86 |  | 9301.76 | 86 |  | 9301.76 | 78 |  | 8436.48 | 86 |  | 9301.76 | 78 |  | 8436.48 | 902 |  | 105996.8
|  | DB-03 854 |  |  | 203954 |  | Curtis | Conkey | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
[7 empty] | David | Ellsworth | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
|  | DB-03 |  |  |  |  | Ryan | Miller | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
|  | DB-03 801 |  |  | 434518 |  | Anna | McColloch | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
|  | DB-03 854 |  |  | 205898 |  | Matt | Stoos | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
|  | DB-04 |  |  |  |  | Chris | Davis | 1 |  | 212000 | 108.16 |  |  |  |  | 0 | 156 |  | 16872.96 | 164 |  | 17738.24 | 148 |  | 16007.68 | 164 |  | 17738.24 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 172 |  | 18603.52 | 156 |  | 16872.96 | 172 |  | 18603.52 | 156 |  | 16872.96 | 1804 |  | 211993.6
[15 empty] | 0 |  | 0 | 1131 |  | 122328.96 | 1189 |  | 128602.24 | 1073 |  | 116055.68 | 1189 |  | 128602.24 | 1247 |  | 134875.52 | 1247 |  | 134875.52 | 1131 |  | 122328.96 | 1247 |  | 134875.52 | 1247 |  | 134875.52 | 1131 |  | 122328.96 | 1247 |  | 134875.52 | 1131 |  | 122328.96 | 13079 |  | 1536953.6
[54 empty] | Total Reim | With Fees | 1713687.7509
[54 empty] | Grand | Total | 6989998.7109
PID
|  | DB-04 801 |  |  | 205989 |  | Doug | Parsons | 0.5 |  | 128987.7 | 144.93 |  |  |  |  | 0 | 78 |  | 11304.54 | 82 |  | 11884.26 | 74 |  | 10724.82 | 82 |  | 11884.26 | 86 |  | 12463.98 | 86 |  | 12463.98 | 78 |  | 11304.54 | 86 |  | 12463.98 | 86 |  | 12463.98 | 78 |  | 11304.54 | 86 |  | 12463.98 | 117 |  | 16956.81 | 902 |  | 147683.67
|  | DE-03 301 |  |  | 434849 |  | Scott | Patrick | 0.5 |  | 98069.1 | 110.19 |  |  |  |  | 0 | 78 |  | 8594.82 | 82 |  | 9035.58 | 74 |  | 8154.06 | 82 |  | 9035.58 | 86 |  | 9476.34 | 86 |  | 9476.34 | 78 |  | 8594.82 | 86 |  | 9476.34 | 86 |  | 9476.34 | 78 |  | 8594.82 | 86 |  | 9476.34 | 78 |  | 8594.82 | 902 |  | 107986.2
|  | DB-03 854 |  |  | 203954 |  | Curtis | Conkey | 1 |  | 184069.8 | 103.41 |  |  |  |  | 0 | 156 |  | 16131.96 | 164 |  | 16959.24 | 148 |  | 15304.68 | 164 |  | 16959.24 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 156 |  | 16131.96 | 1804 |  | 202683.6
[7 empty] | David | Ellsworth | 1 |  | 137166.8 | 77.06 |  |  |  |  | 0 | 156 |  | 12021.36 | 164 |  | 12637.84 | 148 |  | 11404.88 | 164 |  | 12637.84 | 172 |  | 13254.32 | 172 |  | 13254.32 | 156 |  | 12021.36 | 172 |  | 13254.32 | 172 |  | 13254.32 | 156 |  | 12021.36 | 172 |  | 13254.32 | 156 |  | 12021.36 | 1804 |  | 151037.6
|  | DB-03 |  |  |  |  | Ryan | Miller | 1 |  | 184069.8 | 103.41 |  |  |  |  | 0 | 156 |  | 16131.96 | 164 |  | 16959.24 | 148 |  | 15304.68 | 164 |  | 16959.24 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 156 |  | 16131.96 | 1804 |  | 202683.6 | [9 empty] | 206820
|  | DB-03 801 |  |  | 434518 |  | Anna | McColloch | 1 |  | 184069.8 | 103.41 |  |  |  |  | 0 | 156 |  | 16131.96 | 164 |  | 16959.24 | 148 |  | 15304.68 | 164 |  | 16959.24 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 156 |  | 16131.96 | 1804 |  | 202683.6
|  | DB-03 854 |  |  | 205898 |  | Matt | Stoos | 1 |  | 184069.8 | 103.41 |  |  |  |  | 0 | 156 |  | 16131.96 | 164 |  | 16959.24 | 148 |  | 15304.68 | 164 |  | 16959.24 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 156 |  | 16131.96 | 1804 |  | 202683.6
|  | DB-04 |  |  |  |  | Chris | Davis | 1 |  | 184069.8 | 103.41 |  |  |  |  | 0 | 156 |  | 16131.96 | 164 |  | 16959.24 | 148 |  | 15304.68 | 164 |  | 16959.24 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 172 |  | 17786.52 | 156 |  | 16131.96 | 172 |  | 17786.52 | 156 |  | 16131.96 | 1804 |  | 202683.6
[7 empty] | Catherine | [7 empty] | 0 |  | 0 | 1092 |  | 112580.52 | 1148 |  | 118353.88 | 1036 |  | 106807.16 | 1148 |  | 118353.88 | 1204 |  | 124127.24 | 1204 |  | 124127.24 | 1092 |  | 112580.52 | 1204 |  | 124127.24 | 1204 |  | 124127.24 | 1092 |  | 112580.52 | 1204 |  | 124127.24 | 1131 |  | 118232.79 | 12628 |  | 1420125.47
|  | Summer |  |  |  |  | Nathan | Singleton | [45 empty] | Total Reim | With Fees | 1594475.3734
|  | December/Summer Intern |  |  |  |  | Daniel | [46 empty] | Grand | Total | 6870786.3334
|  | Spring |  |  |  |  | Larry
[54 empty] | DC Labor & Travel |  | 5276310.96
[21 empty] | 630464.64 | [23 empty] | 210000 | [8 empty] | x.035 |  | 184670.8836 | [9 empty] | Old fees
[16 empty] | 791070.53 |  |  |  |  | 12609.2928 | [28 empty] | 1594475.3734 |  |  |  | x.027 |  | 142460.3959
[15 empty] | 2363 | 15821.4106 |  |  |  |  | 12866.6253 | [28 empty] | 980000 |  |  |  | Gov cost |  | 1536953.6
[15 empty] | G&A | 57823.84 | [32 empty] | 612500 | 862475.3734 |  |  |  | gov+G&A |  | 1679413.9959
[15 empty] | fees | 73645.2506 | [31 empty] | received | 732000 | 1077649.1157 |  |  |  | gov+G&Ax.02 |  | 1713687.7509
[16 empty] | 717425.2794 | [37 empty] | abov-gov cost |  | 176734.1509 | [9 empty] | new fees
[49 empty] | 7 month Reim need | 1077649.1157
[49 empty] | 7 month DC need | 2818375.31

## nSI rate comp (hidden)
| TO 11 |  | TO 20 |  |  | Delta
|  | 8/26/17-8/25/18 |  | 5/9/17-5/8/18 | 5/9/18-5/8/19
Kirk | Program/Systems Analyst V | 114.44 | Engineer III | 80.41 | 81.86 | -32.58
TenBrink | Program/Systems Analyst VII | 128.15 | Program/Systems Analyst III | 96.5 | 98.23 | -29.92
McIntosh | Program/Systems Analyst VII | 128.15 | Program/Systems Analyst V | 119.47 | 121.62 | -6.53
Dent | Program/Systems Analyst IX | 164.03 | Senior Engineer III | 203.14 | 206.8 | 42.77
Tyler | Program/Systems Analyst IX | 164.03 | Program/Systems Analyst VI | 127.17 | 129.46 | -34.57
Grimmett | Program/Systems Analyst IX | 164.03 | Engineer VIII | 151.06 | 153.78 | -10.25
Boswell | Program/Systems Analyst IX | 164.03 | Program/Systems Analyst IX | 155.47 | 158.27 | -5.76
Tucker | Program/Systems Analyst IX | 164.03 | Subject Matter Expert I | 174.23 | 177.37 | 13.34
-63.5

## FY19 CONTRACT ACTIONS
TO 20 | Cost Center | TIN Letters | MIPR | MIPR AMOUNT | PoP Start | PoP End | MOD | AWARD | SLIN | SLIN |  | HOURS | PRON | WBS | PAN
[10 empty] | LABOR | TRAVEL
TT2120190024 |  | - | HQ0147967210 | 2141623.52 | 2018-11-21 | 2019-10-31 | 38 | 2018NOV30 |  | 0002ME | 0003DD | 15276 | R2933914RV | D.0002019.210 | R20029119
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z
|  |  |  | 2141623.52 | [5 empty] | 0 | 0 | 15276
WBS | Cost Center | TIN | MIPR | MIPR AMOUNT | POP Start | POP End |  | AWARD Date
LETTER
A.0039976.7.3 | 40488166 | - | HQ0147966843 | 791070.53 | 2018-11-21 | 2018-10-31 |  | 2018-11-21
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z

## COL Report
Direct Cite | [5 empty] | Reimbursable | [5 empty] | DC Travel
| Spend Plan | Monthly Accruals | Cumulative Accruals | Funded | Planned Ceiling |  | Spend Plan | Monthly Accruals | Cumulative Accruals | Funded | Planned Ceiling |  | Spend Plan | Monthly Accruals | Cumulative Accruals | Funded | Planned Ceiling
2018-11-15 | 0 | 0 | 0 | 2126483.52 | 5239974.96 | 2018-11-15 | 85200.37 | 85200.37 | 85200.37 | 791070.53 | 1737492.33 | 2018-11-15 | 0 | 0 | 0 | 15140 | 36336
2018-12-15 | 412601.28 | 202148.65 | 202148.65 | 2126483.52 | 5239974.96 | 2018-12-15 | 207529.33 | 92883.99 | 178084.36 | 791070.53 | 1737492.33 | 2018-12-15 | 3028 | 3412.26 | 3412.26 | 15140 | 36336
2019-01-15 | 846361.6 | 347778.02 | 549926.67 | 2126483.52 | 5239974.96 | 2019-01-15 | 336131.57 | 113826.56 | 291910.92 | 791070.53 | 1737492.33 | 2019-01-15 | 6056 | 1614.02 | 5026.28 | 15140 | 36336
2019-02-15 | 1237803.84 | 291269.24 | 841195.91 | 2126483.52 | 5239974.96 | 2019-02-15 | 452187.25 | 117747.06 | 409657.98 | 791070.53 | 1737492.33 | 2019-02-15 | 9084 | 1997.31 | 7023.59 | 15140 | 36336
2019-03-15 | 1671564.16 |  | 841195.91 | 2126483.52 | 5239974.96 | 2019-03-15 | 580789.49 |  | 409657.98 | 791070.53 | 1737492.33 | 2019-03-15 | 12112 |  | 7023.59 | 15140 | 36336
2019-04-15 | 2126483.52 |  | 841195.91 | 2126483.52 | 5239974.96 | 2019-04-15 | 715665.01 |  | 409657.98 | 791070.53 | 1737492.33 | 2019-04-15 | 15140 |  | 7023.59 | 15140 | 36336
2019-05-15 | 2587033.72 |  | 841195.91 |  | 5239974.96 | 2019-05-15 | 850540.53 |  | 409657.98 |  | 1737492.33 | 2019-05-15 | 18168 |  | 7023.59 |  | 36336
2019-06-15 | 3006718.96 |  | 841195.91 |  | 5239974.96 | 2019-06-15 | 972869.49 |  | 409657.98 |  | 1737492.33 | 2019-06-15 | 21196 |  | 7023.59 |  | 36336
2019-07-15 | 3469448.84 |  | 841195.91 |  | 5239974.96 | 2019-07-15 | 1107745.01 |  | 409657.98 |  | 1737492.33 | 2019-07-15 | 24224 |  | 7023.59 |  | 36336
2019-08-15 | 3932613.52 |  | 841195.91 |  | 5239974.96 | 2019-08-15 | 1242620.53 |  | 409657.98 |  | 1737492.33 | 2019-08-15 | 27252 |  | 7023.59 |  | 36336
2019-09-15 | 4353994.48 |  | 841195.91 |  | 5239974.96 | 2019-09-15 | 1364949.49 |  | 409657.98 |  | 1737492.33 | 2019-09-15 | 30280 |  | 7023.59 |  | 36336
2019-10-15 | 4818594 |  | 841195.91 |  | 5239974.96 | 2019-10-15 | 1499825.01 |  | 409657.98 |  | 1737492.33 | 2019-10-15 | 33308 |  | 7023.59 |  | 36336
2019-11-15 | 5239974.96 |  | 841195.91 |  | 5239974.96 | 2019-11-15 | 1622153.97 |  | 409657.98 |  | 1737492.33 | 2019-11-15 | 36336 |  | 7023.59 |  | 36336
Travel | 36336 |  | 841195.91 |  | 5239974.96 | P_Fees | 176751.9898 | 409657.98 | 1212495.99 |  |  | Total | 36336 |  | 29312.41
Total | 5276310.96 | 841195.91 | 4435115.05 |  |  | P_Total | 1737492.33
3028
2084773.32
791070.53
15511.19
57823.84
23552.99
96888.02
694182.51
73335.03

## Hours
Direct Cite Hours
|  |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov
Labor Category | Company | FTE | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
Program Analyst VI | Analytix, LLC | 1 | 156 | 92 | 164 | 173 | 148 | 145.5 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Program Analyst III | Analytix, LLC | 2 | 312 | 275.5 | 328 | 338.5 | 296 | 318 | 328 |  | 344 |  | 344 |  | 312 |  | 344 |  | 344 |  | 312 |  | 344 |  | 312
Engineer/Scientist VII | DESE Research, Inc. | 1 | 156 | 20.5 | 164 | 165 | 148 | 143.5 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Engineer III | nou Systems, Inc. | 1 | 156 | 139.5 | 164 | 168 | 148 | 146.5 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Program/Systems Analyst III | nou Systems, Inc. | 1 | 156 | 134 | 164 | 227 | 148 | 152 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Program/Systems Analyst VI | nou Systems, Inc. | 3 | 468 | 107 | 492 | 312 | 444 | 274 | 492 |  | 516 |  | 516 |  | 468 |  | 516 |  | 516 |  | 468 |  | 516 |  | 468
Senior Engineer III | nou Systems, Inc. | 2 | 312 | 132.5 | 328 | 171 | 296 | 138.5 | 328 |  | 344 |  | 344 |  | 312 |  | 344 |  | 344 |  | 312 |  | 344 |  | 312
Engineer VIII | nou Systems, Inc. | 3 | 468 | 238 | 492 | 404.5 | 444 | 379 | 492 |  | 516 |  | 516 |  | 468 |  | 516 |  | 516 |  | 468 |  | 516 |  | 468
Program/Systems Analyst IX | nou Systems, Inc. | 2 | 312 | 205.5 | 328 | 335.5 | 296 | 253.5 | 328 |  | 344 |  | 344 |  | 312 |  | 344 |  | 344 |  | 312 |  | 344 |  | 312
Subject Matter Expert I | nou Systems, Inc. | 1 | 156 | 79.5 | 164 | 168 | 148 | 136.5 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Program/Systems Analyst V | nou Systems, Inc. | 1 | 156 | 0 | 164 | 0 | 148 | 0 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Program/Systems Analyst l | nou Systems, Inc. | 1 | 156 | 130 | 164 | 54 | 148 | 0 | 164 |  | 172 |  | 172 |  | 156 |  | 172 |  | 172 |  | 156 |  | 172 |  | 156
Cumulative - Direct Cite Hours |  |  | Cumulative-Dec |  | Cumulative-Jan |  | Cumulative-Feb |  | Cumulative-Mar |  | Cumulative-Apr |  | Cumulative-May |  | Cumulative-Jun |  | Cumulative-Jul |  | Cumulative-Aug |  | Cumulative-Sep |  | Cumulative-Oct |  | Cumulative-Nov |  | Ceiling
Labor Category | Company | FTE | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
Program Analyst VI | Analytix, LLC | 1 | 156 | 92 | 320 | 265 | 468 | 410.5 | 632 | 410.5 | 804 | 410.5 | 976 | 410.5 | 1132 | 410.5 | 1304 | 410.5 | 1476 | 410.5 | 1632 | 410.5 | 1804 | 410.5 | 1960 | 410.5 | 1960
Program Analyst III | Analytix, LLC | 2 | 312 | 275.5 | 640 | 614 | 936 | 932 | 1264 | 932 | 1608 | 932 | 1952 | 932 | 2264 | 932 | 2608 | 932 | 2952 | 932 | 3264 | 932 | 3608 | 932 | 3920 | 932 | 3920
Engineer/Scientist VII | DESE Research, Inc. | 1 | 156 | 20.5 | 320 | 185.5 | 468 | 329 | 632 | 329 | 804 | 329 | 976 | 329 | 1132 | 329 | 1304 | 329 | 1476 | 329 | 1632 | 329 | 1804 | 329 | 1960 | 329 | 1960
Engineer III | nou Systems, Inc. | 1 | 156 | 139.5 | 320 | 307.5 | 468 | 454 | 632 | 454 | 804 | 454 | 976 | 454 | 1132 | 454 | 1304 | 454 | 1476 | 454 | 1632 | 454 | 1804 | 454 | 1960 | 454 | 1960
Program/Systems Analyst III | nou Systems, Inc. | 1 | 156 | 134 | 320 | 361 | 468 | 513 | 632 | 513 | 804 | 513 | 976 | 513 | 1132 | 513 | 1304 | 513 | 1476 | 513 | 1632 | 513 | 1804 | 513 | 1960 | 513 | 1960
Program/Systems Analyst VI | nou Systems, Inc. | 3 | 468 | 107 | 960 | 419 | 1404 | 693 | 1896 | 693 | 2412 | 693 | 2928 | 693 | 3396 | 693 | 3912 | 693 | 4428 | 693 | 4896 | 693 | 5412 | 693 | 5880 | 693 | 5880
Senior Engineer III | nou Systems, Inc. | 2 | 312 | 132.5 | 640 | 303.5 | 936 | 442 | 1264 | 442 | 1608 | 442 | 1952 | 442 | 2264 | 442 | 2608 | 442 | 2952 | 442 | 3264 | 442 | 3608 | 442 | 3920 | 442 | 3920
Engineer VIII | nou Systems, Inc. | 3 | 468 | 238 | 960 | 642.5 | 1404 | 1021.5 | 1896 | 1021.5 | 2412 | 1021.5 | 2928 | 1021.5 | 3396 | 1021.5 | 3912 | 1021.5 | 4428 | 1021.5 | 4896 | 1021.5 | 5412 | 1021.5 | 5880 | 1021.5 | 5880
Program/Systems Analyst IX | nou Systems, Inc. | 2 | 312 | 205.5 | 640 | 541 | 936 | 794.5 | 1264 | 794.5 | 1608 | 794.5 | 1952 | 794.5 | 2264 | 794.5 | 2608 | 794.5 | 2952 | 794.5 | 3264 | 794.5 | 3608 | 794.5 | 3920 | 794.5 | 3920
Subject Matter Expert I | nou Systems, Inc. | 1 | 156 | 79.5 | 320 | 247.5 | 468 | 384 | 632 | 384 | 804 | 384 | 976 | 384 | 1132 | 384 | 1304 | 384 | 1476 | 384 | 1632 | 384 | 1804 | 384 | 1960 | 384 | 1960
Program/Systems Analyst V | nou Systems, Inc. | 1 | 156 | 0 | 320 | 0 | 468 | 0 | 632 | 0 | 804 | 0 | 976 | 0 | 1132 | 0 | 1304 | 0 | 1476 | 0 | 1632 | 0 | 1804 | 0 | 1960 | 0 | 1960
Program/Systems Analyst l | nou Systems, Inc. | 1 | 156 | 130 | 320 | 184 | 468 | 184 | 632 | 184 | 804 | 184 | 976 | 184 | 1132 | 184 | 1304 | 184 | 1476 | 184 | 1632 | 184 | 1804 | 184 | 1960 | 184 | 1960
Engineer III | 14
Program/Systems Analyst III | -45
Program/Systems Analyst VI | 711
Senior Engineer III | 494
Engineer VIII | 382.5
Program/Systems Analyst IX | 141.5
Subject Matter Expert I | 84
Program/Systems Analyst V | 468
Program/Systems Analyst l | 284
|  |  | Prog/Sys Analyst IX |  | Prog/Sys Analyst VI |  | Prog/Sys Analyst V |  | Prog/Sys Analyst III |  | Prog/Sys Analyst l
|  |  | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
|  | Dec | 312 | 205.5 | 468 | 107 | 156 | 0 | 156 | 134 | 156 | 130
|  | Jan | 640 | 541 | 960 | 419 | 320 | 0 | 320 | 361 | 320 | 184
|  | Feb | 936 | 794.5 | 1404 | 693 | 468 | 0 | 468 | 513 | 468 | 184
|  | Mar | 1264 | 794.5 | 1896 | 693 | 632 | 0 | 632 | 513 | 632 | 184
|  | Apr | 1608 | 794.5 | 2412 | 693 | 804 | 0 | 804 | 513 | 804 | 184
|  | May | 1952 | 794.5 | 2928 | 693 | 976 | 0 | 976 | 513 | 976 | 184
|  | Jun | 2264 | 794.5 | 3396 | 693 | 1132 | 0 | 1132 | 513 | 1132 | 184
|  | Jul | 2608 | 794.5 | 3912 | 693 | 1304 | 0 | 1304 | 513 | 1304 | 184
|  | Aug | 2952 | 794.5 | 4428 | 693 | 1476 | 0 | 1476 | 513 | 1476 | 184
|  | Sep | 3264 | 794.5 | 4896 | 693 | 1632 | 0 | 1632 | 513 | 1632 | 184
|  | Oct | 3608 | 794.5 | 5412 | 693 | 1804 | 0 | 1804 | 513 | 1804 | 184
|  | Nov | 3920 | 794.5 | 5880 | 693 | 1960 | 0 | 1960 | 513 | 1960 | 184
|  |  | Senior Engineer III |  | Engineer VIII |  | Engineer III |  | Subject Matter Expert I
|  |  | Planned | Worked | Planned | Worked | Planned | Worked | Planned | Worked
|  | Dec | 312 | 132.5 | 468 | 238 | 156 | 139.5 | 156 | 79.5
|  | Jan | 640 | 303.5 | 960 | 642.5 | 320 | 307.5 | 320 | 247.5
|  | Feb | 936 | 442 | 1404 | 1021.5 | 468 | 454 | 468 | 384
|  | Mar | 1264 | 442 | 1896 | 1021.5 | 632 | 454 | 632 | 384
|  | Apr | 1608 | 442 | 2412 | 1021.5 | 804 | 454 | 804 | 384
|  | May | 1952 | 442 | 2928 | 1021.5 | 976 | 454 | 976 | 384
|  | Jun | 2264 | 442 | 3396 | 1021.5 | 1132 | 454 | 1132 | 384
|  | Jul | 2608 | 442 | 3912 | 1021.5 | 1304 | 454 | 1304 | 384
|  | Aug | 2952 | 442 | 4428 | 1021.5 | 1476 | 454 | 1476 | 384
|  | Sep | 3264 | 442 | 4896 | 1021.5 | 1632 | 454 | 1632 | 384
|  | Oct | 3608 | 442 | 5412 | 1021.5 | 1804 | 454 | 1804 | 384
|  | Nov | 3920 | 442 | 5880 | 1021.5 | 1960 | 454 | 1960 | 384
|  |  | Program Analyst VI |  | Program Analyst III
|  |  | Planned | Worked | Planned | Worked
|  | Dec | 156 | 92 | 312 | 275.5
|  | Jan | 320 | 265 | 640 | 614
|  | Feb | 468 | 410.5 | 936 | 932
|  | Mar | 632 | 410.5 | 1264 | 932
|  | Apr | 804 | 410.5 | 1608 | 932
|  | May | 976 | 410.5 | 1952 | 932
|  | Jun | 1132 | 410.5 | 2264 | 932
|  | Jul | 1304 | 410.5 | 2608 | 932
|  | Aug | 1476 | 410.5 | 2952 | 932
|  | Sep | 1632 | 410.5 | 3264 | 932
|  | Oct | 1804 | 410.5 | 3608 | 932
|  | Nov | 1960 | 410.5 | 3920 | 932
Engineer/Scientist VII
|  |  | Planned | Worked
|  | Dec | 156 | 20.5
|  | Jan | 320 | 185.5
|  | Feb | 468 | 329
|  | Mar | 632 | 329
|  | Apr | 804 | 329
|  | May | 976 | 329
|  | Jun | 1132 | 329
|  | Jul | 1304 | 329
|  | Aug | 1476 | 329
|  | Sep | 1632 | 329
|  | Oct | 1804 | 329
|  | Nov | 1960 | 329

## DT Report
Effort | Performer/Contractor | MIPR # | Obligations | Invoiced | Accruals | DAI Expenditures | Projected Funds Exhaust Date | Comments/Notes
BMDS OTA Direct Cite | AMCOM Express TO20 | HQ0147862623 | 2054051.84
BMDS OTA OGA/Fees | AMRDEC
Total | [6 empty] | 0
| MIPR# | TDN# | Amount | Type | Use

## EOM Nov Drill
Cumulative - Direct Cite Hours | Cumulative-Dec |  | Dec-Delta | Cumulative-Jan |  | Jan-Delta | Cumulative-Feb |  | Feb-Delta
Labor Category | Planned | Worked |  | Planned | Worked |  | Planned | Worked
Program Analyst VI | 156 | 92 | 64 | 320 | 265 | 55 | 468 | 410.5 | 57.5
Program Analyst III | 312 | 275.5 | 36.5 | 640 | 614 | 26 | 936 | 932 | 4
Engineer/Scientist VII | 156 | 20.5 | 135.5 | 320 | 185.5 | 134.5 | 468 | 329 | 139
Engineer III | 156 | 139.5 | 16.5 | 320 | 307.5 | 12.5 | 468 | 454 | 14
Program/Systems Analyst III | 156 | 134 | 22 | 320 | 361 | -41 | 468 | 513 | -45
Program/Systems Analyst VI | 468 | 107 | 361 | 960 | 419 | 541 | 1404 | 693 | 711
Senior Engineer III | 312 | 132.5 | 179.5 | 640 | 303.5 | 336.5 | 936 | 442 | 494
Engineer VIII | 468 | 238 | 230 | 960 | 642.5 | 317.5 | 1404 | 1021.5 | 382.5
Program/Systems Analyst IX | 312 | 205.5 | 106.5 | 640 | 541 | 99 | 936 | 794.5 | 141.5
Subject Matter Expert I | 156 | 79.5 | 76.5 | 320 | 247.5 | 72.5 | 468 | 384 | 84
Program/Systems Analyst V | 156 | 0 | 156 | 320 | 0 | 320 | 468 | 0 | 468
Program/Systems Analyst l | 156 | 130 | 26 | 320 | 184 | 136 | 468 | 184 | 284
| Cumulative-Mar | Cumulative-Apr | Cumulative-May | Cumulative-Jun | Cumulative-Jul | Cumulative-Aug | Cumulative-Sep | Cumulative-Oct | Cumulative-Nov | Cumulative | Cumulative | Cumulative | Cumulative | Min 1960 | Min 1920 | Plan
Labor Category | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Unworked | Funded | Unfunded | Credit | Required | Required | EOM Nov
Program Analyst VI | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 57.5 | 1098.5 | 1058.5 | 1098.5
Program Analyst III | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920 | 2984 | 1608 | 2312 | 4 | 2308 | 2268 | 2308
Engineer/Scientist VII | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 139 | 1017 | 977 | 993
Engineer III | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 14 | 1142 | 1102 | 1102
Program/Systems Analyst III | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | -45 | 1201 | 1161 | 1161
Program/Systems Analyst VI | 1896 | 2412 | 2928 | 3396 | 3912 | 4428 | 4896 | 5412 | 5880 | 4476 | 2412 | 3468 | 711 | 2757 | 2717 | 2717
Senior Engineer III | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920 | 2984 | 1608 | 2312 | 494 | 1818 | 1778 | 1778
Engineer VIII | 1896 | 2412 | 2928 | 3396 | 3912 | 4428 | 4896 | 5412 | 5880 | 4476 | 2412 | 3468 | 382.5 | 3085.5 | 3045.5 | 3045.5
Program/Systems Analyst IX | 1264 | 1608 | 1952 | 2264 | 2608 | 2952 | 3264 | 3608 | 3920 | 2984 | 1608 | 2312 | 141.5 | 2170.5 | 2130.5 | 2130.5
Subject Matter Expert I | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 84 | 1072 | 1032 | 1032
Program/Systems Analyst V | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 468 | 688 | 648 | 648
Program/Systems Analyst l | 632 | 804 | 976 | 1132 | 1304 | 1476 | 1632 | 1804 | 1960 | 1492 | 804 | 1156 | 284 | 872 | 832 | 832
Plan
Labor Category | Hours | Rates | Funding
Program Analyst VI | 1098.5 | 129.58 | 142343.63
Program Analyst III | 2308 | 107.9 | 249033.2
Engineer/Scientist VII | 993 | 189.15 | 187825.95
Engineer III | 1102 | 83.33 | 91829.66
Program/Systems Analyst III | 1161 | 100 | 116100
Program/Systems Analyst VI | 2717 | 131.79 | 358073.43
Senior Engineer III | 1778 | 210.52 | 374304.56
Engineer VIII | 3045.5 | 156.55 | 476773.025
Program/Systems Analyst IX | 2130.5 | 161.12 | 343266.16
Subject Matter Expert I | 1032 | 180.56 | 186337.92
Program/Systems Analyst V | 648 | 123.81 | 80228.88
Program/Systems Analyst l | 832 | 70.63 | 58764.16
|  | Total Labor | 2664880.575
|  | Travel | 35000
|  | Surge | 118494.735
|  | Total | 2818375.31

## nSI realignment (hidden)
[5 empty] | CURRENT | ADJ | NEW
PROG |  | LABOR CATEGORY | CONTRACTOR | LOE | HOURS | HOURS | HOURS
OTA | CATEGORY | Systems Analyst V | nou Systems, Inc. | 1 | 452 | -149 | 303
OTA | CATEGORY | Program Analyst VII | nou Systems, Inc. | 1.5 | 187 | 206 | 393
OTA | CATEGORY | Program Analyst IX | nou Systems, Inc. | 5 | 782 | -57 | 725
|  |  |  | 7.5 | 1421 | 0 | 1421